## Gantt Chart
Final Project — Gantt Chart (Mar 6 – Mar 9)
Task | Category | Mar 6 (Fri) | Mar 7 (Sat) | Mar 8 (Sun) | Mar 9 (Mon)
Code Review & Bug Fixes | Code | ▌ | ▌
Test All Features | Code | ▌ | ▌
Clean Up Codebase | Code |  | ▌
Write Final Report | Report | ▌ | ▌
Prepare README / Docs | Report |  | ▌
Assemble Submission Files | Submit |  |  | ▌
Final Check & Verification | Submit |  |  | ▌
Project Showcase | Showcase |  |  |  | ▌
Legend
Code | Report | Submit | Showcase